PROJECT PROPOSAL

COMPREHENSIVE FEASIBILITY STUDIES FOR MAIZE VALUE ADDITION VENTURES

‘’Transforming Market Volatility into Sustainable Competitive Advantage: A Strategic Roadmap for MarketBridge Ltd's Agro-Industrial Diversification’’

Prepared for: The Managing Director MarketBridge Ltd, Evergreen Mall, Abuja, FCT

Prepared by: P3 Consulting Ltd

Date: January 08, 2026

Table of Contents

1.0 EXECUTIVE SUMMARY	3

2.0 INTRODUCTION: THE STRATEGIC IMPERATIVE FOR MARKETBRIDGE LTD	4

2.1 The P3 Consulting Advantage: Local Intelligence, Global Standards	4

2.2 Our Understanding of Your Strategic Crossroads	4

3.0 SITUATION ANALYSIS: THE MAIZE COMMODITY PRICE VULNERABILITY	5

3.1 Detailed Analysis of Price Volatility Drivers in Niger State	5

3.2 The Strategic Case for Vertical Integration	5

4.0 PROPOSED VALUE ADDITION PATHWAYS: FROM SCREENING TO SHORTLIST	6

4.1 Comprehensive Portfolio of Maize Processing Options	6

4.2 Multi-Criteria Analysis & Selection Methodology	6

4.3 Detailed Profile of Three Prioritized Investment Options	8

5.0 SCOPE OF WORK: FOUR-PILLAR FEASIBILITY FRAMEWORK	9

5.1	PILLAR 1: MARKET & COMMERCIAL VIABILITY ANALYSIS	9

5.2 PILLAR 2: TECHNICAL & OPERATIONAL VIABILITY ANALYSIS	10

5.3 PILLAR 3: FINANCIAL & ECONOMIC VIABILITY ANALYSIS	10

5.4 PILLAR 4: MANAGEMENT, SOCIO-ECONOMIC & RISK VIABILITY ANALYSIS	11

6.1 PHASE 1: DIAGNOSTIC SCOPING & INCEPTION (Weeks 1-2)	12

6.2 PHASE 2: INTENSIVE FIELD & DESK RESEARCH (Weeks 3-7)	12

6.3 PHASE 3: DATA SYNTHESIS & FINANCIAL MODELING (Weeks 8-10)	13

6.4 PHASE 4: VALIDATION, REPORTING & FINALIZATION (Weeks 11-12)	14

7.0 PROJECT GOVERNANCE & TEAM COMPOSITION	14

8.0 DELIVERABLES: THE DECISION-MAKER'S TOOLKIT	15

9.0 DETAILED PROJECT TIMELINE & MILESTONES	16

10.0 INVESTMENT BUDGET & COMMERCIAL TERMS	16

11.0 CONCLUSION & STRATEGIC PATH FORWARD	17

1.0 EXECUTIVE SUMMARY

MarketBridge Ltd’s established success in maize production within Niger State has now encountered a fundamental market challenge: the structural vulnerability to unpredictable commodity price cycles. This volatility directly threatens revenue stability, profit margins, and long-term business sustainability. However, within this challenge lies a transformative opportunity.

P3 Consulting Ltd, with over 20 years of embedded agribusiness expertise in Niger State, proposes a definitive strategic intervention: a comprehensive feasibility study program to guide MarketBridge Ltd’s evolution from a primary producer to a value-added agro-processor. This initiative is designed to systematically de-risk your diversification into processing and identify the most profitable, sustainable, and strategically aligned venture.

Our research will focus on three high-potential, shortlisted processing avenues:

- Option A (Staple Food Anchor): An Integrated Modern Maize Milling Plant producing premium branded flour, semolina, and grits for the massive, recession-resilient staple food market.

- Option B (Protein Value Chain Integration): An Animal Feed Production Facility addressing Nigeria's critical feed deficit and leveraging Niger State’s growing livestock sector.

- Option C (Consumer Brand Play): A Maize-Based Snack Food Production Line entering the high-margin, fast-moving consumer goods (FMCG) sector with branded, innovative products.

Our Distinctive Approach: Leveraging the integrated capabilities of the P3 Group, our analysis transcends conventional consultancy. We combine:

- Core Advisory (P3 Consulting): Rigorous market and financial analysis from our team with 95+ years of cumulative experience.

- Technology Insights (P3 Innovation Hub): Digital tools for data collection, supply chain modelling, and tech-enabled operational planning.

- Market Ground-Truth (P3 Delish): Real-world FMCG operational insights, consumer behaviour understanding, and product development practicalities.

1

Final Deliverables – Your Strategic Toolkit: You will receive a complete package enabling confident investment decisions:

- Three detailed, standalone feasibility reports with bankable financial models (5-year projections, NPV, IRR, ROI).

- A comparative executive dashboard for side-by-side evaluation of all options.

- Risk-mitigated implementation roadmaps and investor-ready documentation.

- A digital repository of all primary research data.

Project Investment: The total fee for this 12-week, comprehensive study is ₦9,500,000 (exclusive of 7.5% VAT), structured across three milestone-based payments. This represents a strategic investment in knowledge, designed to de-risk the subsequent capital expenditure (projected at 50-100x this amount) and ensure MarketBridge Ltd’s successful transition into a resilient, diversified agro-industrial enterprise.

P3 Consulting Ltd is not merely a service provider; we are your strategic partner in Niger State’s agricultural transformation, committed to delivering actionable intelligence for your sustainable growth.

2.0 INTRODUCTION: THE STRATEGIC

IMPERATIVE FOR MARKETBRIDGE

LTD

2.1 The P3 Consulting Advantage: Local Intelligence, Global Standards
P3 Consulting Ltd is a premier, wholly Nigerian-owned advisory firm headquartered in the heart of Niger State, Minna. Our mission is to drive inclusive, technology-enabled economic development by empowering institutions and strengthening value chains. Our 95+ years of cumulative team experience is demonstrated through a proven track record of delivering transformative projects for a prestigious clientele including GIZ, the World Bank, USAID, WEMA Bank PLC, and Heifer International.

Our unique, three-dimensional consulting model under the P3 Group ecosystem provides an unparalleled perspective:

P3 Consulting Ltd (The Strategist): Provides core advisory services in agribusiness development, project design, and institutional strengthening.

2

- P3 Innovation Hub (The Technologist): Develops and deploys digital solutions, data analytics platforms, and tech-enabled tools for operational efficiency.

- P3 Delish (The Operator): Our social enterprise FMCG outlet serves as a live laboratory, offering ground-truth insights into consumer preferences, supply chain logistics, food processing, and micro-enterprise management.

This integrated structure ensures that our feasibility study for MarketBridge Ltd is not an academic exercise but a practical, commercially astute blueprint grounded in operational reality and market veracity.

2.2 Our Understanding of Your Strategic Crossroads

MarketBridge Ltd has demonstrated excellence in primary maize production. However, this very success has created a strategic dependency on commodity markets characterized by volatility. The decision to explore value addition is both courageous and necessary. It represents a fundamental shift from being

a price-taker to becoming a price-maker and value-creator.

This proposal is designed to systematically illuminate this path forward. We acknowledge the complexity, significant capital requirements, and operational challenges inherent in this transition. Our role is to eliminate uncertainty through meticulous research, robust analysis, and clear, data-driven recommendations, thereby providing the Management and Board of MarketBridge Ltd with the confidence to commit to a transformative investment.

3.0 SITUATION ANALYSIS: THE MAIZE COMMODITY PRICE VULNERABILITY

3.1 Detailed Analysis of Price Volatility Drivers in Niger State
MarketBridge Ltd's current business model is exposed to a confluence of systemic risks:

- Macro-Level Drivers: National harvest outcomes, federal import/export policies, cross-border smuggling, fluctuating exchange rates affecting input costs, and speculative trading on commodity exchanges.

Mesio-Level (Regional) Drivers: North-Central regional production trends, logistica

3

l bottlenecks (bad roads, high transport costs), and the dominant role of aggregators and middlemen who control market information and pricing.

- Micro-Level (Farm-Gate) Drivers: Lack of adequate on-farm storage leading to forced sales during glut periods, limited direct access to institutional buyers or processors, and the sale of maize as an undifferentiated commodity with no premium for quality.

This multi-layered volatility results in unpredictable revenue streams, compressed profit margins during downturns, and an inability to plan long-term investments with certainty.

3.2 The Strategic Case for Vertical Integration

Establishing a processing arm is the most effective strategic response to this vulnerability. Value addition fundamentally alters the business equation by:

- Margin Stabilization & Enhancement: Converting raw maize into finished products captures multiple layers of margin currently earned by processors, distributors, and retailers.

- Demand Diversification: Creating access to distinct markets—household consumers (flour/snacks), livestock farmers (feed), and food industries (grits)—that are not perfectly correlated.

- Brand Equity & Customer Loyalty: Developing branded products (e.g., "MarketBridge Premium Maize Flour") builds intangible asset value and reduces competition to mere price.

- Supply Chain Control & Efficiency: Internalizing processing improves quality control, reduces post-harvest losses, and allows for the utilization of all grain grades.

- Strategic Risk Hedging: The processing business can act as a natural hedge; when farm-gate maize prices are low, processing margins can improve, and vice-versa.

4

4.0 PROPOSED VALUE ADDITION PATHWAYS: FROM SCREENING TO SHOR

3

TLIST

4.1 Comprehensive Portfolio of Maize Processing Options

2

| Category | Specific Venture | Complexity | Capital Intensity | Market Nature | Key Success Factor |
| --- | --- | --- | --- | --- | --- |
| Primary Food | Dry Milling (Flour, Semolina) | Medium | Medium-High | Mass Market, B2C/B2B | Distribution Network, Branding |
|  | Wet Milling (Starch, Sweeteners) | Very High | Very High | Industrial, B2B | Tech Expertise, Scale, Capital |
| Animal Nutrition | Composite Feed Mill | Medium-High | Medium-High | B2B (Commercial Farms) | Formulation Science, Sales Force |
|  | Pre-Mix/Ingredient Production | High | High | B2B (Other Millers) | R&D, Quality Control |
| Consumer Foods | Extruded Snacks (Corn Puffs) | Medium | Medium | Mass Market, B2C | Marketing, Product Innovation |
|  | Instant Ogi/Tuwo Flour | Low-Medium | Low-Medium | Niche/B2C | Quality Consistency, Packaging |
| Industrial | Bioethanol/Beverages | Extremely High | Extremely High | B2B/Regulated | 5 Po 3 licy Support, Mega-Scale |

4.2 Multi-Criteria Analysis & Selection Methodology

We applied a weighted decision matrix to screen the long-list, prioritizing options that align with MarketBridge Ltd’s assets, Niger State’s market dynamics, and investment pragmatism.

| Criteria (Weight) | Description | Assessment Focus |
| --- | --- | --- |
| Market Demand & Growth (25%) | Current size, projected growth rate, and accessibility of the target market within a 300km radius of Niger State. | Consumer surveys, trade data, demographic trends. |
| Strategic Fit & Synergy (20%) | Utilization of existing maize production, alignment with current operations, and potential for by-product synergy. | Analysis of your current yield, quality, and operational assets. |
| Capital Efficiency & Funding (20%) | Reasonableness of initial CAPEX, availability of debt financing, and grant/soft loan opportunities. | Liaison with CBN, BOA, and commercial banks. |
| Technical & Operational Attainability (15%) | Availability of technology, ease of maintenance, skill requirements, and infrastructure needs. | Supplier consultations, site audits, skills gap analysis. |
| Profitability & Risk-Adjusted Return (20%) | Projected margins, ROI, payback period, and inherent business risks. | Preliminary financial modelling and risk assessment. |

6

4.3 Detailed Profile of Three Prioritized Investment Options

OPTION A: INTEGRATED MODERN MAIZE MILLING PLANT

- Core Concept: A semi-automated processing facility transforming raw maize into:

  - Branded Whole & Degerminated Maize Flour (for Tuwo Masara and Akamu/Ogi)

  - Maize Semolina (for Couscous, pasta, and breakfast cereals)

  - Maize Grits (for breweries, cereal manufacturers)

Strategic Rationale:

  - Defensive Market Play: Targets the non-discretionary staple food segment, ensuring consistent demand.

  - High Synergy: Directly consumes your core product. Allows for premium pricing for quality.

  - Scalable & Modular: Can start with a 10-20MT/day capacity and expand.

  - By-Product Valorisation: Germ (for oil/cake) and bran are valuable feed ingredients, creating a natural link to Option B.

OPTION B: ANIMAL FEED PRODUCTION FACILITY

- Core Concept: A complete feed mill producing scientifically formulated, pelleted/mashed feeds:

  - Poultry Feed Rations (Starter, Grower, Finisher, Layer Mash)

  - Aquaculture (Fish Feed)

7

Ruminant Supplements (Dairy Meal, Feedlot Concentrates)

- Strategic Rationale:

  - Addressing a Critical Gap: Nigeria faces a >2 million MT annual feed deficit. Niger State's livestock population is a captive initial market.

  - B2B Model with Recurring Revenue: Feed is a consumable with regular purchase cycles.

  - Strong Policy Support: Aligns with national protein sufficiency goals, improving access to CBN and state government financing.

  - Input Integration: Maize constitutes 50-65% of feed formula, ensuring a primary market for your produce.

OPTION C: MAIZE-BASED SNACK FOOD PRODUCTION LINE

- Core Concept: An extrusion cooking line producing expanded, flavoured snacks:

  - Cheese Balls, Chili Twists, Barbecue Puffs in 20g-100g branded, stand-up pouches.

- Strategic Rationale:

  - High-Growth, High-Margin Segment: The snack food market is growing at >10% annually, driven by urbanization and youth demographics.

  - Brand-Building Opportunity: Offers the strongest potential for creating a beloved consumer brand with loyal customers.

  - Innovation Platform: Allows for easy line extensions (new flavours, fortified variants, mixed packs).

Superior Margins: Value addition from raw maize to packaged snack yields significant gross margins.

8

5.0 SCOPE OF WORK: FOUR-PILLAR FEASIBILITY FRAMEWORK

  - PILLAR 1: MARKET & COMMERCIAL VIABILITY ANALYSIS

- Comprehensive Market Assessment:

  - Demand Quantification: Estimate Total Addressable Market (TAM), Serviceable Available Market (SAM), and Serviceable Obtainable Market (SOM) for each product in Niger, Abuja, Kaduna, and Kogi.

  - Consumer Behaviours Study: For Options A & C: 400 household surveys, 8 Focus Group Discussions (FGDs) to unpack purchasing triggers, brand perception, packaging preferences, and price sensitivity.

  - Institutional/B2B Demand Mapping: For Option B: In-depth interviews with 50+ poultry farmers, cattle herders, and feed retailers to understand formulation preferences, procurement cycles, and credit terms.

- Competitive Intelligence & Positioning:

  - Competitor Profiling: Map 5-7 key competitors per option, analysing their product portfolio, pricing, distribution strength, marketing spend, and perceived weaknesses.

  - Gap Analysis & USP Formulation: Identify unmet consumer/farmer needs and crystallize a compelling Unique Selling Proposition (USP) for the MarketBridge Ltd brand in each segment.

- Supply Chain & Route-to-Market Strategy:

  - Input Sourcing Matrix: Develop a database of reliable suppliers for fortificants, additives, flavours, packaging (flexible films, sacks), and spare parts.

  - Distribution Channel Economics: Model the cost-to-serve and profitability of various channels: direct sales to large farms/hotels, distributors, open market wholesalers, and modern retail (supermarkets).

Regulatory & Marketing Pathway:

9

  - Certification Roadmap: Detailed step-by-step guide to obtaining NAFDAC product registration, SONCAP certification, and any NECC requirements.

  - Go-to-Market Blueprint: Outline launch marketing activities, branding concept notes, and promotional strategies for Year 1.

5.2 PILLAR 2: TECHNICAL & OPERATIONAL VIABILITY ANALYSIS

- Process Engineering & Technology Audit:

  - Capacity Planning: Determine optimal installed capacity based on market absorption and scalability. Model CAPEX for 10MT/day, 20MT/day, and 50MT/day scenarios for milling.

  - Equipment Specification & Sourcing: Provide detailed technical sheets for major equipment (cleaners, destoners, degerminators, hammer mills, extruders, mixers, pellet mills, packaging machines) with 3 potential supplier quotes (Local, Chinese, European).

  - Factory Layout Design: Create preliminary CAD-assisted layout plans optimizing workflow, hygiene, material handling, and future expansion.

- Raw Material Security & Logistics:

  - Maize Procurement Model: Analyse your current production vs. processing needs. Design a procurement strategy involving own-farm supply, out-grower networks, and spot market purchases, including required storage (silo) capacity.

  - Ancillary Input Sourcing: Identify and pre-quality suppliers for key non-maize inputs specific to each option (e.g., soybean meal, limestone, premixes for feed; flavours, oils for snacks).

- Site & Infrastructure Suitability Study:

Location Analysis: Comparative SWOT analysis of establishing the plant on your existing farm site versus a leased plot in a designated industrial cluster (e.g., Maikunkele,

10

Bida).

Infrastructure Due Diligence: Detailed report on power supply (proposal for solar-diesel hybrid system), water source and treatment, effluent disposal, waste management, and road network adequacy.

11

- Human Capital & Organizational Design:

  - Manpower Plan: Define the organizational structure, job descriptions, and staffing levels for management, technical, production, and administrative roles.

  - Skills Audit & Training Framework: Identify critical skill gaps in the local labor market and propose a tailored training program, potentially in collaboration with government schemes (NYSC, NDE).

5.3 PILLAR 3: FINANCIAL & ECONOMIC VIABILITY ANALYSIS

- Detailed Capital Expenditure (CAPEX) Modelling:

  - Fixed Asset Schedule: Itemized costing for land (if purchased), civil works, factory building, machinery, vehicles, office equipment, and pre-operative expenses (incorporation, licenses, training).

- Operating Expenditure (OPEX) Forecasting:

  - Monthly Cost Build-Up: Detailed projections for raw materials (monthly consumption based on recipes), utilities, direct labor, factory overheads, marketing, administration, royalty/technical fees, and financial costs.

- Revenue & Profitability Projections:

  - Pricing Strategy & Sales Forecast: Develop a tiered pricing model (ex-factory, distributor, retail). Build a month-by-month sales volume forecast for Years 1-3, considering realistic capacity utilization ramp-up (Year 1: 45%, Year 2: 65%, Year 3: 80%).

- Financial Statement Projections & Investment Appraisal:

  - 5-Year Integrated Financial Model: Generate projected Income Statements, Cash Flow Statements, and Balance Sheets.

  - Key Investment Metrics: Calculate and interpret: Payback Period (PBP), Net Present Value (NPV) at 18% and 22% discount rates, Internal Rate of Return (IRR), and Return on Investment (ROI).

- Risk-Adjusted Financial Analysis:

  - Sensitivity Analysis: A "Tornado Diagram" showing the impact of ±20% variation in maize cost, selling price, and capacity utilization on NPV and IRR.

  - Scenario Planning: Develop and model financials for "Base Case," "Optimistic," and "Pessimistic" scenarios.

- Funding Strategy & Capital Structure:

  - Financing Plan: Recommend an optimal debt-to-equity ratio. Provide a term sheet structure for potential debt.

  - Financier Mapping: Identify and profile 5-7 specific banks/DFIs (e.g., CBN via Participating Financial Institution (PFI), BOA, NIRSAL, commercial bank agri-desks) with applicable loan products, rates, and requirements.

5.4 PILLAR 4: MANAGEMENT, SOCIO-ECONOMIC & RISK VIABILITY ANALYSIS

- Implementation & Management Plan:

  - Detailed Project Roadmap: A 24-month activity-based implementation schedule from Final Investment Decision (FID) to commercial operation, highlighting critical path activities.

  - Project Governance Model: Recommend a project steering committee structure and reporting lines for the implementation phase.

- Socio-Economic & Environmental Impact Assessment:

Impact Metrics: Quantify direct, indirect, and induced job creation. Estimate secondary

12

economic benefits for local service providers and suppliers.

  - Environmental & Social (E&S) Screening: Identify potential E&S impacts (noise, dust, wastewater) and propose simple, cost-effective mitigation measures in line with international best practices (IFC Performance Standards).

- Comprehensive Risk Management Framework:

  - Risk Register: Document all identified strategic, operational, financial, and compliance risks, assessing their likelihood and potential impact.

  - Mitigation & Contingency Actions: For each high-priority risk, propose specific, actionable mitigation strategies and contingency plans.

6.0 METHODOLOGY: A PHASED, EVIDENCE-BASED APPROACH FOR MARKETBRIDGE LTD

Our methodology is a rigorous, four-phase process designed to generate actionable intelligence, not just data. It combines quantitative precision with qualitative depth, leveraging our local presence for efficient execution.

6.1 PHASE 1: DIAGNOSTIC SCOPING & INCEPTION (Weeks 1-2)

- Activity 1.1: Strategic Kick-off & Alignment Workshop: A half-day session with MarketBridge Ltd’s management at your Abuja office or farm site to align on core strategic objectives, risk tolerance, and specific success metrics for the study.

- Activity 1.2: Internal Data Harvest: We will request and analyse key internal documents: 3 years of production records, cost structures, land titles/topographical maps of your Niger State farm, existing financial statements, and any prior market assessments.

- Activity 1.3: Preliminary Stakeholder Mapping: Identification of key informants and institutions in Niger State relevant to each option (e.g., National Association of Nigerian Poultry Farmers (NANPF) Niger Chapter, Maize Growers Association, Ministry of Agriculture, NAFDAC state office).

Activity 1.4: Finalization of Research Instruments: Development and pre-testing of tailored

13

survey questionnaires, FGD guides, and interview protocols for farmers, consumers, retailers, and industrial buyers.

6.2 PHASE 2: INTENSIVE FIELD & DESK RESEARCH (Weeks 3-7)

- Activity 2.1: Macro & Sectoral Desk Research:

  - Analysis of national data from NBS, CBN, and FAO on maize production, consumption, and trade.

  - Policy review: Analysis of the National Agricultural Technology and Innovation Policy (NATIP), CBN’s Maize Aggregation Scheme, and Niger State’s agricultural development plans.

  - Global and regional benchmarking of processing technologies and efficiency metrics.

- Activity 2.2: Primary Market Intelligence Collection (Concurrent Streams):

  - Stream A (Consumer & Retail): Teams deployed to Minna, Bida, Suleja, and Abuja. Conduct 400 in-person surveys at major markets (e.g., Bosso, Kure) and modern retail outlets. Facilitate 8 FGDs segmented by income level and household type.

  - Stream B (B2B & Institutional): Teams interview 30+ commercial poultry/ livestock farmers in Paiko, Gawu-Babangida, and Kotongora. Conduct structured interviews with 20+ feed distributors, flour wholesalers, and potential institutional buyers (boarding schools, prisons).

  - Stream C (Competitive & Supply Chain): Mystery shopping and trade audits of competitor products. Interviews with equipment dealers in Kaduna and Kano, packaging suppliers in Lagos, and input (premix, flavor) importers.

- Activity 2.3: Technical & Site-Specific Assessments:

Site Analysis: Detailed topographic and infrastructure assessment of your proposed farm site and 2-3 alternative industrial cluster locations. This includes soil testing for construction, water source yield tests, and grid power stability analysis over a 72-hour period.

14

  - Technology Scouting: Virtual and physical meetings with shortlisted equipment suppliers (e.g., locally fabricated hammer mills vs. imported Turkish degerminators) to gather definitive quotes and specifications.

6.3 PHASE 3: DATA SYNTHESIS & FINANCIAL MODELING (Weeks 8-10)

- Activity 3.1: Data Processing & Analysis:

  - All survey data will be cleaned, coded, and analysed using statistical software (SPSS) to establish confidence intervals, cross-tabulations, and correlation analysis.

  - Qualitative data from FGDs and interviews will be thematically analysed to extract nuanced insights on brand perception and non-price decision factors.

- Activity 3.2: Dynamic Financial Model Construction:

  - Development of three separate, interlinked but standalone financial models in Microsoft Excel. Each model will feature:

    - A "Dashboard" tab summarizing key inputs and outputs.

    - A "Detailed Assumptions" tab where every variable (from maize price to packing film cost per gram) can be modified.

    - "Scenario Managers" to instantly toggle between Base, Optimistic, and Pessimistic cases.

    - Fully integrated financial statements projecting monthly for Year 1 and annually for Years 2-5.

    - Automated generation of NPV, IRR, and Payback Period.

- Activity 3.3: Risk & Sensitivity Modelling:

  - Formal risk scoring using a Probability-Impact Matrix.

Construction of sensitivity analysis tables and tornado charts to visually demonstrate the financial impact of key variable fluctuations.

15

6.4 PHASE 4: VALIDATION, REPORTING & FINALIZATION (Weeks 11-12)

- Activity 4.1: Draft Report Compilation & Internal Review: Our senior team will synthesize all findings into three comprehensive draft reports.

- Activity 4.2: Stakeholder Validation Workshop: We will present the draft findings, key financial metrics, and preliminary recommendations in a half-day workshop with MarketBridge Ltd’s management team. This is a critical feedback loop to ensure our analysis aligns with your operational realities.

- Activity 4.3: Report Finalization & Toolkits Preparation: Incorporating your feedback, we will produce the polished final reports, finalize the financial models, and design the executive comparative dashboard.

- Activity 4.4: Final Presentation & Knowledge Transfer: A formal presentation to the Board/Executive Committee, followed by a session to walk your nominated staff through the financial models, ensuring you can use them for ongoing scenario analysis.

7.0 PROJECT GOVERNANCE & TEAM COMPOSITION

7.1 The P3 Integrated Value Proposition for MarketBridge Ltd
This project will leverage the full spectrum of P3 Group capabilities, ensuring MarketBridge Ltd benefits from a 360-degree perspective:

- P3 Consulting (Core Lead): Provides the project management, agricultural economics expertise, and strategic framing.

P3 Innovation Hub (Tech & Data Lead): Will manage all digital data collection using KoBoToolbox/ODK, provide data analytics support, and advise on potential process automation and digital inventory management systems relevant to the final chosen option.

16

- P3 Delish (Market Reality Check): Will provide practical insights on packaging design appeal, shelf-life challenges, and distributor relationship management drawn from direct FMCG experience in Minna.

7.2 Key Personnel Profiles & Roles

Our team is a blend of seasoned experts and dynamic local professionals with direct Niger State networks.

| Name & Role | Key Qualifications & Relevant Experience | Specific Responsibilities for MarketBridge Ltd Project |
| --- | --- | --- |
| Nosa Osunde Project Sponsor | 20+ years in development consulting. Expert in participatory project design and stakeholder management. Led GIZ SEDIN’s Organizational Development stream. | Overall quality assurance, client relationship management at the MD level, and final sign-off on all deliverables. |
| Dr. Samuel Biodun Ikuborije Project Director | MBBS, MSc - Enterprise Development. Designed the financing product for WEMA Bank/GIZ-EAT. Specializes in agri-finance and value chain analysis. | Lead architect of the financial models and funding strategy. Oversees all economic analysis and ensures bankability of the final recommendations. |
| Aliyu Abdulrahman Project Manager | SME support and M&E expert. Managed BDS delivery for 1,100+ entrepreneurs under GIZ. Strong data systems background. | Day-to-day project execution, timeline/budget adherence, lead on market research design, and primary author of the final reports. |
| Yusuf Inuwa Senior Field Coordinator | Business Coach with 10+ years in Niger State. Deep networks with farmer groups and agri-entrepreneurs. Worked on USAID-FtF and GIZ SEDIN. | Leads all field enumeration teams, secures stakeholder interviews, conducts FGDs, and provides ground-truth verification of all market data. |

17

8.0 DELIVERABLES: THE DECISION-MAKER'S TOOLKIT

Upon successful completion, MarketBridge Ltd will receive the following comprehensive deliverables, designed as practical tools for immediate use:

- Three (3) Bound Feasibility Study Reports: Professionally printed and bound volumes (3 hard copies each), plus searchable PDFs. Each report (approx. 80-100 pages) will be structured as follows:

  - Executive Summary with Key Recommendation

  - Detailed Market Analysis with Survey Data Appendices

  - Technical Specifications and Plant Design Chapter

  - Comprehensive Financial Analysis with Full Assumptions

  - Risk Assessment & Mitigation Plan

  - Detailed Implementation Roadmap (24-month)

  - Full Regulatory Compliance Checklist

- Three (3) Dynamic Financial Models (Microsoft Excel Files): Fully formula-driven, unlocked models allowing MarketBridge Ltd to:

  - Adjust key assumptions (prices, costs, capacity) and instantly see the impact on profitability.

  - Run custom “what-if” scenarios beyond our base cases.

  - Use the models directly for engaging with banks and investors.

- Comparative Investment Dashboard (PowerPoint & Excel): A one-page summary matrix comparing all three options across 15+ key metrics (Total CAPEX, IRR, Payback Period, Job Creation, Market Risk Score, etc.), providing an at-a-glance decision aid for the Board.

Final Board Presentation Pack (PowerPoint): A concise, visually compelling 25-slide deck

18

summarizing the process, findings, and a clear, prioritized recommendation for the way forward.

- Digital Research Repository: A password-protected cloud folder containing:

  - All raw, anonymized survey data (Excel/SPSS files).

  - Copies of equipment quotations and technical brochures.

  - Photographs from site assessments and competitor products.

  - Scanned copies of relevant policy documents.

9.0 DETAILED PROJECT TIMELINE & MILESTONES

The project will be executed over a 12-week period from date of mobilization.

Key Milestones:

- Milestone 1 (End of Week 2): Completion of Inception Phase; submission of final work plan and data collection tools.

- Milestone 2 (End of Week 7): Completion of all primary field research.

- Milestone 3 (End of Week 10): Submission of Draft Feasibility Reports and Models for client review.

Milestone 4 (End of Week 12): Delivery of all Final Deliverables and project close-out.

19

10.0 INVESTMENT BUDGET & COMMERCIAL TERMS

10.1 Detailed Budget Breakdown

The total investment for this comprehensive study is ₦9,500,000.00 (Nine Million, Five Hundred Thousand Naira Only), exclusive of 7.5% VAT. This represents exceptional value given the depth of parallel analysis across three complex options.

| Budget Line Item | Detailed Description & Justification | Amount (₦) |
| --- | --- | --- |
| A. Professional & Technical Fees | Fees for the core project team (Sponsor, Director, Manager, Field Coordinator) for 12 weeks of dedicated effort. Includes strategic oversight, financial modelling, and report authorship. | 5,200,000 |
| B. Field Research & Logistics | Costs for 8 enumerators for 4 weeks, including training, stipends, and transportation. Travel, accommodation, and per diem for core team during field weeks across multiple locations. Logistics for Focus Group Discussions (venue, refreshments, participant incentives). | 2,150,000 |
| C. Technical Consultations & Data | Fees for specialized technical advisors (Engineers, Architects etc). Purchase of relevant industry reports/data. Software licenses for advanced data analysis (SPSS). Communication costs (airtime, internet). | 1,000,000 |
| D. Report Production & Presentation | Professional graphic design, CAD and final reports. Preparation of digital deliverable repository on branded USB drives. | 400,000 |
| E. Project Administration & Contingency | Project management overhead, client meeting logistics, bank/ stakeholder liaison costs. A 5% contingency to manage unforeseen field challenges or scope clarifications. | 750,000 |
|  | SUB-TOTAL (Exclusive of VAT) | 9,500,000 |
|  | Value Added Tax (VAT) at 7.5% | 712,500 |
|  | GRAND TOTAL 20 | 10,212,500 |

11.0 CONCLUSION & STRATEGIC PATH FORWARD

MarketBridge Ltd stands at a definitive inflection point. The cyclical vulnerability inherent in primary commodity production is not merely a seasonal challenge but a structural constraint on profitability, growth, and long-term enterprise value. The strategic response, vertical integration into value-added processing, is both necessary and transformative.

This comprehensive proposal from P3 Consulting Ltd outlines a meticulous, evidence-based pathway to de-risk this critical strategic pivot. Our approach is designed to transform uncertainty into clarity and opportunity into a bankable investment plan. By conducting parallel, in-depth feasibility studies on the three most promising avenues, Integrated Maize Milling, Animal Feed Production, and Snack Food Manufacturing, we will equip your leadership with a definitive decision-making toolkit.

Our value proposition is rooted in more than just analysis; it is built on local embeddedness, practical operational insight from the P3 Group, and a proven track record in making agribusinesses finance-ready. We understand the soil of Niger State as well as the nuances of its markets.

The deliverable will be a clear, comparative, and financially-validated roadmap. You will not receive vague recommendations, but specific, actionable plans complete with:

- Validated market entry strategies.

- Technically sound plant specifications.

- Investor-grade financial projections (NPV, IRR, ROI).

- A clear view of risks and their mitigants.

P3 Consulting Ltd is ready to partner with you to navigate this journey. Let us collaborate to transform MarketBridge Ltd from a respected producer into a dominant, integrated agro-industrial leader, securing sustainable profits and building a legacy of resilience for the future.

21